## BRK-AUDIT-01
Activity ID | Activity Name | WBS | Activity Type | Original Duration (d) | Calendar | Predecessors | Constraint Type | Constraint Date
BA1000 | Contract Award | Milestones | Start Milestone | 0 | FACTORY-5D
BA1010 | Project Kick-off | Project Management | Task Dependent | 1 | FACTORY-5D | BA1000
BA1020 | Project Management and Reporting | Project Management | Task Dependent | 120 | FACTORY-5D | BA1010
BA1030 | Review Specification | Engineering | Task Dependent | 4 | FACTORY-5D | BA1010
BA1040 | Develop Single Line Diagram | Engineering | Task Dependent | 10 | FACTORY-5D | BA1030
BA1050 | Internal Design Review | Engineering | Task Dependent | 2 | FACTORY-5D | BA1040
BA1060 | Issue SLD for Client Approval | Engineering | Task Dependent | 1 | FACTORY-5D | BA1040,BA1050
BA1070 | Client Approval - SLD | Engineering | Task Dependent | 5 | FACTORY-5D | BA1060FS+45
BA1080 | Develop GA Drawings | Engineering | Task Dependent | 12 | FACTORY-5D | BA1070
BA1090 | Develop Schematics | Engineering | Task Dependent | 15 | FACTORY-5D | BA1080SS+3
BA1100 | Issue Shop Drawings | Engineering | Task Dependent | 2 | FACTORY-5D | BA1090
BA1110 | Client Approval - Shop Drawings | Engineering | Task Dependent | 10 | FACTORY-5D | BA1100
BA1120 | Design Sign-off | Engineering | Task Dependent | 0 | FACTORY-5D | BA1110
BA1130 | Bill of Materials | Engineering | Task Dependent | 5 | FACTORY-5D | BA1080
BA1140 | Order Long Lead Equipment | Procurement | Task Dependent | 2 | FACTORY-5D | BA1120,BA1130
BA1150 | Manufacture and Delivery - ACBs | Procurement | Task Dependent | 120 | FACTORY-5D | BA1140
BA1160 | Delivery - MCCBs and Devices | Procurement | Task Dependent | 45 | CAL-7D | BA1140
BA1170 | Delivery - Copper Busbar | Procurement | Task Dependent | 35 | CAL-7D | BA1140
BA1180 | Delivery - Enclosures | Procurement | Task Dependent | 50 | CAL-7D | BA1140
BA1190 | Goods Inward Inspection | Manufacture | Task Dependent | 2 | FACTORY-5D | BA1180
BA1200 | Erect and Join Cubicles | Manufacture | Task Dependent | 7 | FACTORY-5D | BA1190
BA1210 | Install Earth Bar | Manufacture | Task Dependent | 3 | FACTORY-5D | BA1200
BA1220 | Machine and Install Busbar | Manufacture | Task Dependent | 10 | FACTORY-5D | BA1170,BA1200,BA1210
BA1230 | Busbar Torque and Inspection | Manufacture | Task Dependent | 2 | FACTORY-5D | BA1220
BA1240 | Install ACB Cassettes | Manufacture | Task Dependent | 4 | FACTORY-5D | BA1150,BA1230
BA1250 | Install MCCB Chassis and Devices | Manufacture | Task Dependent | 6 | FACTORY-5D | BA1160,BA1220
BA1260 | Internal Wiring - Power | Manufacture | Task Dependent | 10 | FACTORY-5D | BA1240FS-10,BA1250
BA1270 | Internal Wiring - Control | Manufacture | Task Dependent | 12 | FACTORY-5D | BA1260SS+3
BA1280 | Labelling and Warning Signage | Manufacture | Task Dependent | 4 | FACTORY-5D | BA1270
BA1290 | QA Inspection | Test & Release | Task Dependent | 3 | FACTORY-5D | BA1270
BA1300 | Works Testing | Test & Release | Task Dependent | 8 | FACTORY-5D | BA1290
BA1310 | Factory Acceptance Test | Test & Release | Task Dependent | 3 | FACTORY-5D | BA1300 | Mandatory Finish | 14-Nov-25
BA1320 | Client Defect List Issued | Test & Release | Task Dependent | 1 | FACTORY-5D | BA1310
BA1330 | Rectify FAT Defects | Test & Release | Task Dependent | 5 | FACTORY-5D | BA1310SS
BA1340 | FAT Re-test and Sign-off | Test & Release | Task Dependent | 2 | FACTORY-5D | BA1330
BA1350 | Pack and Crate | Logistics | Task Dependent | 3 | FACTORY-5D | BA1340
BA1360 | Transport to Site | Logistics | Task Dependent | 2 | FACTORY-5D | BA1350
BA1370 | Offload and Set to Position | Site Installation | Task Dependent | 3 | FACTORY-5D | BA1360
BA1380 | Re-join Splits and Busbar | Site Installation | Task Dependent | 5 | SITE-6D | BA1370
BA1390 | Pull LV Power Cables | Site Installation | Task Dependent | 10 | SITE-6D
BA1400 | Glanding and Terminations | Site Installation | Task Dependent | 12 | SITE-6D | BA1380,BA1390
BA1410 | Site QA and Snag | Site Installation | Task Dependent | 3 | SITE-6D | BA1400SF
BA1420 | Pre-Energisation Testing | Commissioning | Task Dependent | 6 | SITE-6D | BA1410
BA1430 | Energisation | Commissioning | Task Dependent | 1 | SITE-6D |  | Start On | 02-Feb-26
BA1440 | Load Testing | Commissioning | Task Dependent | 4 | SITE-6D | BA1430
BA1450 | O&M Manuals and As-Builts | Commissioning | Task Dependent | 10 | FACTORY-5D | BA1400
BA1460 | Practical Completion | Milestones | Finish Milestone | 0 | SITE-6D | BA1440,BA1450 | Finish On or Before | 20-Feb-26

## BRIEF
BRK-AUDIT-01 - Schedule Audit Exercise
Phase 10. Do not open before then.
THE SCENARIO
You have just joined a switchgear manufacturer as their planner. The previous planner left three weeks ago. This is the programme they left behind for a 3200A switchroom package. The client's project director has asked you one question: 'Can I rely on this?'
YOUR TASK
1. Import it into P6 and schedule it (F9).
2. Find every defect. There are FOURTEEN deliberate faults planted in this schedule.
3. For each: name the defect, name the activity, explain the consequence in one sentence.
4. Score the schedule out of 100 using the rubric from your roadmap.
5. Write the review email you would actually send to the person who built it - professional, specific, and not career-ending for them.
HINTS - THE SIX FAMILIES OF DEFECT
Logic faults - open ends, danglers, redundant links, reverse logic, wrong relationship type
Lag abuse - excessive lags, negative lags (leads)
Constraint abuse- hard constraints replacing real logic
Duration faults - excessive durations, zero-duration tasks that should be milestones
Calendar faults - work assigned to a calendar that does not match where it happens
Type faults - activity type that misrepresents how the work behaves
Send me your findings list and I will mark it against the answer key. Anything you miss, I will show you exactly how a reviewer would have caught it.