## START HERE
SWB-CAP-01 - Capstone Activity Pack
4000A Form 4b Switchroom ¦ Data Centre Stage 2 ¦ Award to Practical Completion
118 activities ¦ 10 milestones ¦ 155 relationships ¦ 3 calendars ¦ 9 WBS elements
WHY THIS PACK EXISTS
Typing 118 activities by hand is where most beginners quit. It teaches you nothing except typing. Import this instead and spend your hours on the part that actually makes you employable: the LOGIC, the CALENDARS, and the CRITICAL PATH.
HOW TO USE IT - PHASE 3
Step 1. Build the WBS in P6 by hand from the 'WBS' tab. Nine elements. Do this manually - it takes ten minutes and it is the one structural thing you must feel.
Step 2. Create the three calendars from the 'Calendars' tab BEFORE importing. If the calendars do not exist, P6 will silently drop every activity onto the default calendar and your dates will be wrong.
Step 3. In P6: File > Import > Excel (XLS). Map columns to Activity ID, Activity Name, Activity Type, Original Duration, Calendar. Import the activities WITHOUT relationships first.
Step 4. Add the 155 relationships from the Predecessors column BY HAND. Yes, by hand. This is the single highest-value exercise in the whole course - you cannot learn logic by importing it.
Step 5. Press F9. Read your critical path. Report your finish date back to me.
READING THE PREDECESSORS COLUMN
EN1050 = Finish-to-Start, no lag (the default)
MF1040SS+2 = Start-to-Start with a 2 day lag
SI1100FF+2 = Finish-to-Finish with a 2 day lag
TR1080FS+5 = Finish-to-Start with a 5 day lag
PR1140FF = Finish-to-Finish, no lag
A,B,C = multiple predecessors, comma separated
THE THREE CALENDARS - AND WHY THEY MATTER
FACTORY-5D Mon-Fri, 8h. Your workshop.
SITE-6D Mon-Sat, 10h. Data centre sites run six days.
CAL-7D 7 days, 24h. Supplier lead times and transit run on CALENDAR days, not working days. Putting a 90 day ACB lead time on a 5-day calendar adds about 36 days of pure fiction to your programme. This single mistake is one of the most common in real switchgear schedules.
DELIBERATE OMISSIONS
There are no constraints in this pack, and no resource units. That is intentional. You will add constraints in Phase 3 (and justify every one), resources in Phase 7, and costs in Phase 7-8.

## Activities
Activity ID | Activity Name | WBS Code | WBS Name | Activity Type | Original Duration (d) | Calendar | Predecessors | Primary Resource | Planner Note
MS1000 | Contract Award | SWB-CAP-01.1 | Contract Milestones | Start Milestone | 0 | FACTORY-5D |  |  | Start milestone. No predecessor - this is your project start.
MS1010 | Design Freeze - SLD Approved | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | FACTORY-5D | EN1050 |  | Gate: nothing may be ordered on unapproved design.
MS1020 | All Long-Lead Orders Placed | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | FACTORY-5D | PR1030,PR1050,PR1070,PR1090,PR1110,PR1130 |  | Classic path-convergence milestone. Watch float here.
MS1030 | Enclosures Delivered to Factory | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | FACTORY-5D | PR1140 |  | Interface milestone between procurement and manufacture.
MS1040 | Switchboard Assembly Complete | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | FACTORY-5D | MF1180,MF1190,MF1200 |  | Gate into the test phase.
MS1050 | FAT Pass - Released to Site | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | FACTORY-5D | TR1120 |  | Contractual milestone. Usually a payment trigger.
MS1060 | Delivery to Site Complete | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | SITE-6D | LG1070 |  | Risk transfer point in most contracts.
MS1070 | Cable Terminations Complete | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | SITE-6D | SI1100,SI1110 |  | Gate into commissioning.
MS1080 | Energisation | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | SITE-6D | CX1070 |  | The date the client actually cares about.
MS1090 | Practical Completion | SWB-CAP-01.1 | Contract Milestones | Finish Milestone | 0 | SITE-6D | CX1110 |  | Project finish milestone. Must have no successor.
PM1000 | Project Kick-off Meeting | SWB-CAP-01.2 | Project Management | Task Dependent | 1 | FACTORY-5D | MS1000 | Project Manager | Sets the tone. Schedule is issued here.
PM1010 | Develop Project Execution Plan | SWB-CAP-01.2 | Project Management | Task Dependent | 5 | FACTORY-5D | PM1000 | Project Manager
PM1020 | Develop and Issue Baseline Programme | SWB-CAP-01.2 | Project Management | Task Dependent | 5 | FACTORY-5D | PM1010SS+2 | Planner | You are this resource.
PM1030 | Project Management and Reporting | SWB-CAP-01.2 | Project Management | Level of Effort | 180 | FACTORY-5D | PM1000 | Project Manager | Level of Effort - spans the job, must never drive the critical path.
PM1040 | Project Close-out and Handover Documentation | SWB-CAP-01.2 | Project Management | Task Dependent | 10 | FACTORY-5D | CX1110 | Project Manager
EN1000 | Review Contract Technical Specification | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 5 | FACTORY-5D | PM1000 | Design Engineer
EN1010 | Site Survey - Confirm Switchroom Dimensions | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 2 | FACTORY-5D | PM1000 | Design Engineer | Access constraint: coordinate with builder.
EN1020 | Develop Single Line Diagram (SLD) | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 10 | FACTORY-5D | EN1000 | Design Engineer | The parent document of the whole job.
EN1030 | Internal Design Review - SLD | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 2 | FACTORY-5D | EN1020 | Design Engineer
EN1040 | Issue SLD for Client Approval | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 1 | FACTORY-5D | EN1030 | Design Engineer
EN1050 | Client Approval - SLD | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 10 | FACTORY-5D | EN1040 | Client | Client-controlled duration. Track it: this is where EOT claims are born.
EN1060 | Protection and Metering Schedule | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 8 | FACTORY-5D | EN1050 | Design Engineer
EN1070 | Develop General Arrangement (GA) Drawings | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 12 | FACTORY-5D | EN1050,EN1010 | Draftsperson
EN1080 | Develop Schematic and Wiring Diagrams | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 15 | FACTORY-5D | EN1060SS+3 | Draftsperson
EN1090 | Busbar Sizing and Short Circuit Calculations | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 6 | FACTORY-5D | EN1020 | Design Engineer | AS/NZS 3439 / AS 61439 verification.
EN1100 | Form 4b Segregation Design | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 5 | FACTORY-5D | EN1070SS+5 | Design Engineer
EN1110 | Arc Flash and Internal Arc Containment Design | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 5 | FACTORY-5D | EN1090 | Design Engineer
EN1120 | Cable Schedule and Gland Plate Design | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 6 | FACTORY-5D | EN1070 | Draftsperson
EN1130 | Issue Shop Drawings for Client Approval | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 2 | FACTORY-5D | EN1070,EN1080,EN1100,EN1110,EN1120 | Draftsperson | Path convergence - five predecessors.
EN1140 | Client Approval - Shop Drawings | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 15 | FACTORY-5D | EN1130 | Client | Contracted 10 days. Budget 15. Ask me why in Phase 5.
EN1150 | Incorporate Client Comments | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 5 | FACTORY-5D | EN1140 | Draftsperson
EN1160 | Re-issue Shop Drawings - Approved for Construction | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 2 | FACTORY-5D | EN1150 | Draftsperson
EN1170 | Develop Bill of Materials (BOM) | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 5 | FACTORY-5D | EN1070SS+5 | Design Engineer
EN1180 | Develop Test Procedures and ITP | SWB-CAP-01.3 | Engineering & Design | Task Dependent | 8 | FACTORY-5D | EN1080 | Test Engineer
PR1000 | Compile Long-Lead Item Register | SWB-CAP-01.4 | Procurement | Task Dependent | 3 | FACTORY-5D | EN1020 | Procurement Officer
PR1010 | Request Quotations - 4000A ACBs | SWB-CAP-01.4 | Procurement | Task Dependent | 5 | FACTORY-5D | PR1000 | Procurement Officer
PR1020 | Technical Evaluation - ACBs | SWB-CAP-01.4 | Procurement | Task Dependent | 3 | FACTORY-5D | PR1010 | Design Engineer
PR1030 | Place Order - 4000A ACBs | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | PR1020,EN1050 | Procurement Officer | Do not order before design freeze.
PR1040 | Manufacture and Delivery - 4000A ACBs | SWB-CAP-01.4 | Procurement | Task Dependent | 90 | CAL-7D | PR1030 |  | 90 CALENDAR days - note the 7-day calendar. This is your longest lead item.
PR1050 | Place Order - MCCBs and Distribution Devices | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | EN1170 | Procurement Officer
PR1060 | Manufacture and Delivery - MCCBs | SWB-CAP-01.4 | Procurement | Task Dependent | 45 | CAL-7D | PR1050
PR1070 | Place Order - CTs, VTs and Metering | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | EN1060 | Procurement Officer
PR1080 | Delivery - CTs, VTs and Metering | SWB-CAP-01.4 | Procurement | Task Dependent | 40 | CAL-7D | PR1070
PR1090 | Place Order - Protection Relays and PLC | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | EN1060 | Procurement Officer
PR1100 | Delivery - Protection Relays and PLC | SWB-CAP-01.4 | Procurement | Task Dependent | 60 | CAL-7D | PR1090
PR1110 | Place Order - Copper Busbar | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | EN1090 | Procurement Officer
PR1120 | Delivery - Copper Busbar | SWB-CAP-01.4 | Procurement | Task Dependent | 35 | CAL-7D | PR1110
PR1130 | Place Order - Enclosures and Cubicles | SWB-CAP-01.4 | Procurement | Task Dependent | 1 | FACTORY-5D | EN1160 | Procurement Officer | Needs AFC drawings, not approved-with-comments.
PR1140 | Fabrication and Delivery - Enclosures | SWB-CAP-01.4 | Procurement | Task Dependent | 50 | CAL-7D | PR1130
PR1150 | Procure Wiring, Terminals and Consumables | SWB-CAP-01.4 | Procurement | Task Dependent | 20 | CAL-7D | EN1170 | Procurement Officer
PR1160 | Expedite and Track Long-Lead Deliveries | SWB-CAP-01.4 | Procurement | Level of Effort | 120 | FACTORY-5D | PR1030 | Procurement Officer | Level of Effort.
MF1000 | Factory Bay Allocation and Setup | SWB-CAP-01.5 | Manufacture | Task Dependent | 2 | FACTORY-5D | PR1140FF | Production Supervisor | FF relationship - bay must be ready when steel lands.
MF1010 | Goods Inward Inspection - Enclosures | SWB-CAP-01.5 | Manufacture | Task Dependent | 2 | FACTORY-5D | MS1030,MF1000 | QA Inspector
MF1020 | Enclosure Modification and Cut-outs | SWB-CAP-01.5 | Manufacture | Task Dependent | 5 | FACTORY-5D | MF1010 | Assembler
MF1030 | Powder Coat Touch-up and Cure | SWB-CAP-01.5 | Manufacture | Task Dependent | 3 | FACTORY-5D | MF1020 | Assembler | Cure time is a lag candidate - discuss in Phase 4.
MF1040 | Erect and Join Cubicles 1-4 | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | MF1030 | Assembler
MF1050 | Erect and Join Cubicles 5-8 | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | MF1040SS+2 | Assembler | Crew moves through - classic SS+lag.
MF1060 | Install Earth Bar and Earthing System | SWB-CAP-01.5 | Manufacture | Task Dependent | 3 | FACTORY-5D | MF1040 | Assembler
MF1070 | Machine Main Horizontal Busbar | SWB-CAP-01.5 | Manufacture | Task Dependent | 6 | FACTORY-5D | PR1120,EN1160 | Busbar Fabricator
MF1080 | Install Main Horizontal Busbar | SWB-CAP-01.5 | Manufacture | Task Dependent | 5 | FACTORY-5D | MF1070,MF1050,MF1060 | Busbar Fabricator
MF1090 | Machine and Install Vertical Droppers | SWB-CAP-01.5 | Manufacture | Task Dependent | 6 | FACTORY-5D | MF1080SS+2 | Busbar Fabricator
MF1100 | Apply Busbar Insulation and Phase Barriers | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | MF1090 | Assembler
MF1110 | Busbar Torque and Inspection | SWB-CAP-01.5 | Manufacture | Task Dependent | 2 | FACTORY-5D | MF1100 | QA Inspector | Hold point. Torque records required.
MF1120 | Install 4000A ACB Cassettes | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | PR1040,MF1110 | Assembler | Watch this one - PR1040 is your long lead.
MF1130 | Install MCCB Chassis and Devices | SWB-CAP-01.5 | Manufacture | Task Dependent | 6 | FACTORY-5D | PR1060,MF1090 | Assembler
MF1140 | Install CTs, VTs and Metering | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | PR1080,MF1090 | Assembler
MF1150 | Install Protection Relays and PLC Panel | SWB-CAP-01.5 | Manufacture | Task Dependent | 5 | FACTORY-5D | PR1100,MF1050 | Assembler
MF1160 | Install Form 4b Segregation Barriers | SWB-CAP-01.5 | Manufacture | Task Dependent | 5 | FACTORY-5D | MF1130,MF1120 | Assembler
MF1170 | Internal Wiring - Power Circuits | SWB-CAP-01.5 | Manufacture | Task Dependent | 10 | FACTORY-5D | MF1120,MF1130,PR1150 | Wireman
MF1180 | Internal Wiring - Control and Protection | SWB-CAP-01.5 | Manufacture | Task Dependent | 12 | FACTORY-5D | MF1150,MF1140,MF1170SS+3 | Wireman
MF1190 | Labelling, Schedules and Warning Signage | SWB-CAP-01.5 | Manufacture | Task Dependent | 4 | FACTORY-5D | MF1180SS+5 | Assembler
MF1200 | Install Gland Plates and Cable Zone Fit-out | SWB-CAP-01.5 | Manufacture | Task Dependent | 3 | FACTORY-5D | MF1160 | Assembler
TR1000 | QA Inspection - Mechanical | SWB-CAP-01.6 | Test & Release | Task Dependent | 2 | FACTORY-5D | MS1040 | QA Inspector
TR1010 | QA Inspection - Electrical and Wiring Check | SWB-CAP-01.6 | Test & Release | Task Dependent | 3 | FACTORY-5D | TR1000 | QA Inspector
TR1020 | Continuity and Insulation Resistance Testing | SWB-CAP-01.6 | Test & Release | Task Dependent | 2 | FACTORY-5D | TR1010 | Test Engineer
TR1030 | Primary Injection Testing - Busbar and CTs | SWB-CAP-01.6 | Test & Release | Task Dependent | 3 | FACTORY-5D | TR1020 | Test Engineer
TR1040 | Secondary Injection - Protection Relays | SWB-CAP-01.6 | Test & Release | Task Dependent | 4 | FACTORY-5D | TR1030 | Test Engineer
TR1050 | Functional and Sequence Testing | SWB-CAP-01.6 | Test & Release | Task Dependent | 4 | FACTORY-5D | TR1040 | Test Engineer
TR1060 | Pre-FAT Snag and Rectification | SWB-CAP-01.6 | Test & Release | Task Dependent | 3 | FACTORY-5D | TR1050 | Assembler
TR1070 | Compile FAT Documentation Pack | SWB-CAP-01.6 | Test & Release | Task Dependent | 3 | FACTORY-5D | TR1050SS+2,EN1180 | Test Engineer
TR1080 | Issue FAT Notification to Client | SWB-CAP-01.6 | Test & Release | Task Dependent | 1 | FACTORY-5D | TR1050 | Project Manager | Contract usually requires notice - hence the lag below.
TR1090 | Factory Acceptance Test (FAT) | SWB-CAP-01.6 | Test & Release | Task Dependent | 3 | FACTORY-5D | TR1060,TR1070,TR1080FS+5 | Test Engineer | FS+5 = contractual 5-day notice period.
TR1100 | Client Defect and Punch List Issued | SWB-CAP-01.6 | Test & Release | Task Dependent | 1 | FACTORY-5D | TR1090 | Client
TR1110 | Rectify FAT Defects | SWB-CAP-01.6 | Test & Release | Task Dependent | 5 | FACTORY-5D | TR1100 | Assembler | Duration is an estimate - a risk item, not a fact.
TR1120 | FAT Re-test and Sign-off | SWB-CAP-01.6 | Test & Release | Task Dependent | 2 | FACTORY-5D | TR1110 | Test Engineer
LG1000 | Prepare Packing and Transport Plan | SWB-CAP-01.7 | Logistics | Task Dependent | 3 | FACTORY-5D | TR1070SS | Logistics Coordinator
LG1010 | Disassemble for Transport (Shipping Splits) | SWB-CAP-01.7 | Logistics | Task Dependent | 2 | FACTORY-5D | MS1050 | Assembler
LG1020 | Protective Wrapping and Crating | SWB-CAP-01.7 | Logistics | Task Dependent | 3 | FACTORY-5D | LG1010 | Assembler
LG1030 | Arrange Transport Permits and Escorts | SWB-CAP-01.7 | Logistics | Task Dependent | 5 | FACTORY-5D | LG1000 | Logistics Coordinator | Oversize load - permits have their own lead time.
LG1040 | Load to Transport | SWB-CAP-01.7 | Logistics | Task Dependent | 1 | FACTORY-5D | LG1020,LG1030,SI1000 | Logistics Coordinator | Do not load until site confirms readiness.
LG1050 | Transport to Site | SWB-CAP-01.7 | Logistics | Task Dependent | 2 | CAL-7D | LG1040 | Transport Contractor
LG1060 | Site Offload and Positioning | SWB-CAP-01.7 | Logistics | Task Dependent | 2 | SITE-6D | LG1050 | Crane / Rigger
LG1070 | Goods Inward Inspection at Site | SWB-CAP-01.7 | Logistics | Task Dependent | 1 | SITE-6D | LG1060 | QA Inspector | Damage in transit is found here or never.
SI1000 | Confirm Switchroom Ready (Site Readiness) | SWB-CAP-01.8 | Site Installation | Task Dependent | 1 | SITE-6D | LG1030 | Site Supervisor | Slab, doors, HVAC, roof watertight.
SI1010 | Set Out and Install Plinth / Base Frame | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | SI1000 | Electrician
SI1020 | Set Switchboard to Position | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | MS1060,SI1010 | Crane / Rigger
SI1030 | Re-join Shipping Splits | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | SI1020 | Electrician
SI1040 | Re-make Busbar Joints and Torque | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | SI1030 | Electrician | Torque records again - QA hold point.
SI1050 | Install Site Earthing Connections | SWB-CAP-01.8 | Site Installation | Task Dependent | 2 | SITE-6D | SI1040 | Electrician
SI1060 | Mechanical Fixing and Levelling | SWB-CAP-01.8 | Site Installation | Task Dependent | 2 | SITE-6D | SI1030SS+2 | Electrician
SI1070 | Pull LV Power Cables | SWB-CAP-01.8 | Site Installation | Task Dependent | 10 | SITE-6D | SI1020 | Electrician | Often done by others - interface risk.
SI1080 | Pull Control and Comms Cables | SWB-CAP-01.8 | Site Installation | Task Dependent | 6 | SITE-6D | SI1070SS+3 | Electrician
SI1090 | Glanding and Terminations - Power | SWB-CAP-01.8 | Site Installation | Task Dependent | 8 | SITE-6D | SI1070,SI1050 | Electrician
SI1100 | Glanding and Terminations - Control | SWB-CAP-01.8 | Site Installation | Task Dependent | 6 | SITE-6D | SI1080,SI1090SS+3 | Electrician
SI1110 | Cable Schedule Verification and Labelling | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | SI1100FF+2 | Electrician
SI1120 | Site QA Inspection and Snag | SWB-CAP-01.8 | Site Installation | Task Dependent | 3 | SITE-6D | SI1110 | QA Inspector
CX1000 | Pre-Energisation Inspection | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 2 | SITE-6D | SI1120 | Test Engineer
CX1010 | Insulation Resistance and Continuity - Site | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 3 | SITE-6D | CX1000 | Test Engineer
CX1020 | Apply Protection Settings | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 2 | SITE-6D | CX1010 | Test Engineer
CX1030 | Secondary Injection Verification - Site | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 3 | SITE-6D | CX1020 | Test Engineer
CX1040 | Functional Testing with Upstream Supply | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 3 | SITE-6D | CX1030 | Test Engineer
CX1050 | SCADA / BMS Point-to-Point Verification | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 4 | SITE-6D | CX1030SS+2 | Controls Engineer
CX1060 | Pre-Energisation Safety Review and Permits | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 2 | SITE-6D | CX1040,CX1050 | Site Supervisor | Permit to work. No shortcuts here.
CX1070 | Energisation | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 1 | SITE-6D | CX1060 | Test Engineer
CX1080 | Load Bank / Load Transfer Testing | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 4 | SITE-6D | CX1070 | Test Engineer
CX1090 | Compile and Issue O&M Manuals and As-Builts | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 10 | FACTORY-5D | SI1110 | Draftsperson
CX1100 | Client Training | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 2 | SITE-6D | CX1080 | Test Engineer
CX1110 | Practical Completion Handover | SWB-CAP-01.9 | Testing & Commissioning | Task Dependent | 1 | SITE-6D | CX1080,CX1090,CX1100 | Project Manager

## WBS
WBS Code | WBS Name | Activities | Purpose
SWB-CAP-01 | 4000A Switchroom - Data Centre Stage 2 |  | Project root
SWB-CAP-01.1 | Contract Milestones | 10 | Gates and payment triggers. Kept separate so they never get lost in detail.
SWB-CAP-01.2 | Project Management | 5 | PM effort and reporting. Mostly Level of Effort.
SWB-CAP-01.3 | Engineering & Design | 19 | SLD through to Approved For Construction drawings.
SWB-CAP-01.4 | Procurement | 17 | Orders and supplier lead times. Runs on the 7-day calendar.
SWB-CAP-01.5 | Manufacture | 21 | Factory build. Your home turf.
SWB-CAP-01.6 | Test & Release | 13 | Works testing through FAT sign-off.
SWB-CAP-01.7 | Logistics | 8 | Packing, permits, transport, offload.
SWB-CAP-01.8 | Site Installation | 13 | Setting, joining, cabling, terminations.
SWB-CAP-01.9 | Testing & Commissioning | 12 | Pre-energisation through Practical Completion.

## Calendars
Calendar ID | Working Days | Hours/Day | Hours/Week | Used For | Non-Work Exceptions to Add
FACTORY-5D | Mon-Fri | 8 | 40 | Engineering, procurement admin, manufacture, test, packing | Public holidays; Christmas shutdown 24 Dec - 5 Jan
SITE-6D | Mon-Sat | 10 | 60 | Site installation, commissioning, offload | Public holidays; site shutdown periods; data centre change-freeze windows
CAL-7D | Mon-Sun | 24 | 168 | Supplier lead times, manufacturing at vendor, transit | None. Lead times do not stop for weekends.

## Resources (Phase 7)
Resource ID | Resource Name | Type | Unit | Rate (AUD) | Max Units/Time | Calendar | Notes
PM | Project Manager | Labour | h | 165 | 0.5 | FACTORY-5D | Part time across the job
PLN | Planner | Labour | h | 145 | 0.25 | FACTORY-5D | That is you
DE | Design Engineer | Labour | h | 155 | 2 | FACTORY-5D
DFT | Draftsperson | Labour | h | 110 | 3 | FACTORY-5D | Peak during shop drawings
PO | Procurement Officer | Labour | h | 95 | 1 | FACTORY-5D
ASM | Switchboard Assembler | Labour | h | 92 | 6 | FACTORY-5D | Your main factory constraint
WIR | Wireman | Labour | h | 98 | 5 | FACTORY-5D | Peak resource - watch for over-allocation
BUS | Busbar Fabricator | Labour | h | 105 | 2 | FACTORY-5D | Scarce skill. Only two in the shop.
QA | QA Inspector | Labour | h | 115 | 1 | FACTORY-5D
TE | Test Engineer | Labour | h | 135 | 2 | FACTORY-5D
CE | Controls Engineer | Labour | h | 140 | 1 | SITE-6D
ELE | Site Electrician | Labour | h | 105 | 8 | SITE-6D
SUP | Site Supervisor | Labour | h | 125 | 1 | SITE-6D
BAY | Factory Assembly Bay | Non-Labour | d | 450 | 1 | FACTORY-5D | Hard constraint - you only have one 8-cubicle bay
CRN | Overhead Crane / Rigger | Non-Labour | h | 210 | 1 | SITE-6D
HVT | HV/LV Test Set | Non-Labour | d | 320 | 1 | FACTORY-5D
TRK | Transport (Oversize) | Non-Labour | ea | 8500 | 1 | CAL-7D
ACB | 4000A ACB | Material | ea | 46000 |  |  | Long lead - 90 calendar days
MCB | MCCB Assembly Set | Material | ea | 78000 |  |  | Lot cost across all cubicles
CU | Copper Busbar | Material | kg | 28 |  |  | Price exposed to commodity movement
ENC | Enclosure / Cubicle | Material | ea | 19500 |  |  | 8 cubicles
REL | Protection Relay / PLC Set | Material | ea | 64000